## Projektstrukturplan
Projektstrukturplan
Update: | 10.01.2022
|  |  |  | 2021 |  |  |  |  | 2022
| Tasks | Deadline | Status | August | September | Oktober | November | Dezember | Januar | Februar | March | April | May | June | July
Project management
| Goals (SMART) | 30.09.21 | completed; finish up after meeting on 28.09.
| Strategy (Project plan) | 30.09.21 | completed; finish up after meeting on 28.09.
| Requirements | 30.09.21 | completed; finish up after meeting on 28.09.
Transcriptomics data
| Compile list of databases | 10.10.21 | done
| Compile list of newest publications | 31.10.21 | 14.02.: done; 15.11.: done for GSE
| Create list of transcriptomics data | 31.12.21 | 14.02.: done; 10.01.: first draft done, waiting for review; 15:11.: work in progress
| Sort data into categories | 31.12.21 | 14.02.: done; 10.01.: first draft done, waiting for review; 15:11.: work in progress
| Update gene names into WormBase IDs | 15.03.22 | 31.03.: done; 14.02.: waiting for working package 02; 10.01.: update after first review
Database
| Fix References | 31.05.22
| Update website text | 31.05.22
| Incorporate code changes | 15.07.22
| Update database | 20.07.22
Quality management
| Write script for database search | 31.01.22 | 14.02.: done; changed for better usability; 15.11.: done for GSE
| Write script for automated notification | 31.02.22 | removed
| Write SOP for updating database | 31.07.22 | 14.02.: work-in-progress
| Manage Github | 31.07.22 | 05.05.: created and regularly updated
| Test Runs locally | 31.05.22
| Pilot Study/Test Runs online | 31.07.22

## To-Do
To-Do
done
urgent
rejected
| Task | Deadline | Comment | Who?
| references | 31.07.2022 | 12.03.: references don't work correctly if gene set name is not exactly the same as in reference list -> cannot find some references | Jenny
| Proof of Principle | 31.03.2022 | 12.03.; how to do gene enrichment analysis with Bt data sets; Katja feedback summarizing strain data sets; 02.03.: make list with all microbes in database; ask Katja how to upload data
| Update database | 31.07.2022 | 12.03.: access server done; 22.02.: check where to upload finished database; make last test after update; 17.02.: check if addition of epigenetics leads to problems, check with test analysis that everything works properly | Jenny
| Multiple Categories | 31.07.2022 | 12.03.: WormExp cannot pack data sets in more than one category -> find source file and update | Jenny/Yang
| Kleines Announcement | 31.03.2022 | Zum Abschluss des Updates | Jenny
| Finish SOP for future students | 31.03.2022 | 12.03.: chapter test runs ongoing | Jenny
| Datafinder script anpassen, um es zu automatisieren | 31.03.2022 | 14.02.: no automation, but changed for use for others; 07.10.: including date or other parameter to pre-filter data, etc. | Jenny
| Kategorien anpassen | 31.03.2022 | 14.02.: added category epigenetics; 11.10.: eventuell anpassen von Kategorien für Schlagwörter wie "epigenetics"/"microbiome analysis"/etc.
| Test database | 07.03.2022 | 24.02.: done; 22.02.: generate test sets and test database two times: 1. without updates and 2. with updates; add dataset that includes epigenetics | Jenny
| Create list with transcriptomics data and information | 11.03.2022 | 07.03.: transcriptomic list done; 01.03.: second working package WIP; 14.02.: first working_package done, second in review at Katja; 15.11.: work in progress; Give list to Katja | Jenny
| Write script that updates Wormbase IDs in .txt files | 31.03.2022 | 14.02.: rejected; SimpleMine from Wormbase is way easier | Jenny
| Merge summary files into WormExp_info | 11.03.2022 | 13.03.: done | Jenny
| Update dataset names | 31.03.2022 | 17.02.: done | Jenny
| Create list with dataset names and references | 31.03.2022 | 17.02.: done | Jenny
| Update geneID list (WS283) | 31.03.2022 | 14.02.: done | Jenny
| Change scripts into useable formats | 31.03.2022 | 14.02.: done | Jenny
| Projekt auf Schulenberg Lab Github ziehen | 31.10.2021 | 17.02.: done | Jenny
| Make Stakeholder Slide | 10.10.2021 | 01.10.: done | Jenny
| Make Pilot Study Slide | 31.10.2021 | 20.01.: done | Jenny
| Create list with databases to search through | 10.10.2021 | 01.10.: done; main database is NCBI, | Jenny
| Find out what to look for when deciding which data is useful and which is not | 11.10.2021 | 15.11.: meeting with hinrich to assess current status; 07.10.: write Mail to Katja; ask Hinrich and/or Katja for things to look out for | Jenny
| ArrayExpress database paper extraction | 31.12.2021 | 22.10.: E-MEXP-xx codes are from ArrayExpress. Is there a coding solution or does it have to be searched manually? https://www.ebi.ac.uk/arrayexpress/browse.html | Jenny
| Yang Tag Vergleich Paper | 31.10.2021 | 21.10.: made some query analysis; Aussage Yang: "just do it manually"; 11.10.: Zur Verbesserung der Query (include Zarate-Potes et al. 2020 PLoS Pathogens) | Jenny
| Write datamanagement plan (DMP) for project/database | 31.03.2021 | 14.10.: use of FAIR principles (also see RMDKit by Elixir); Data - everything that is produced (also workflows, etc.); | Jenny
| Use GSE list to check out found data | 10.10.2021 | 07.10.: done; data was transfered to Excel file for further use | Jenny
| Kick-Off meeting Hinrich | 28.09.2021 | 27.09.: done; Appointment: 28.09.21, 16:00 Uhr, Zoom | Jenny
| Learn to work with github | 30.09.2021 | 27.08.: installed git and learned to stage and commit changes. Change was commited as "Start of Project WormExp" with WormSource program saved, as well as the starting information. Next: create GitHub account and upload project in private! | Jenny
| Create GitHub account and transfer WormSource as private project there | 30.09.2021 | done | Jenny
| How do virtual environments work? | 30.09.2021 | 22.09.: done | Jenny
| Learn containisation | 30.09.2021 | 22.09.: probably only important later on for good implementation of optimization. | Jenny
| Get to know database | 31.01.2022 | done; 27.08.: copy made via git ("Start of the WormExp Project") -> rewind possible. Nevertheless, if possible work on it not on an "active" platform. | Jenny
| Check code that is used to upload information in WormSource | 31.01.2022 | done; 27.08.: this code is important to include in textminer/paper picker. | Jenny
| Automate database updates | 31.03.2022 | 20.01.: rejected, too big to keep as sub-project | Jenny
| "Pilot Study" einbauen in Projektstrukturplan | 31.03.2022 | 27.09.: done; Beinhaltet Gespräch mit Yang, kurze Vordemonstrationen des Codes und auch Überlegungen zum genauen Einbau | Jenny
| Send Papa WormExp | 31.10.2021 | 22.09.: done | Jenny
| Reading papers | 31.10.2021 | 15.11.: done -> reading papers is part of gaining data; 27.08.: how is transcriptomics data used? Strength? Weaknesses? Current topics in C. Elegans specific research? | Jenny
| Research new papers | 31.10.2021 | 15.11.: not necessary; Maybe use textmining tools/picker; 27.08.: found github projects like findpaper or paperai (or TwitterBot) that are already programs in python to search through databases. Idea would be simply to get them to work and get new papers automatically send to my email as soon as they are public (https://github.com/KPHippe/Paper_Finder) | Jenny
| Create a new branch in git to work on paper picker/textminder | 31.10.2021 | 30.08.: done locally, move branch to github | Jenny
| Download textminer/paper picker and test it out | 31.12.2021 | 21.10.: serpapi works only with a subscription; https://github.com/maikelronnau/google_scholar_paper_finder, ; 22.09.: see if it leads to more data results than e.g. GEOparse; 01.09.: downloaded package Findpapers | Jenny
| Web application programming (html/javascript/php), logistics, interfaces, etc. (Tomcat) | 31.12.2021 | done | Jenny
| Meet-Up for Tomcat | 31.12.2021 | Meet-Up to get an introduction to Tomcat | Jenny

## Projektstunden
Projektstunden
Update: | 27.09.2021
| Date | Hours | Comments
| 22.07.21 | 0.5 | email correspondence with clients and supporters
| 03.08.21 | 0.5 | meeting with L.Silvas due discuss project plans
| 27.08.21 | 0.5 | outlining project, saving start of project in git
| 09.09.21 | 4 | starting datafinder; pipeline that will automatically send new IDs for review to a person; getting a feel for GSE database and the already existing database content
| 22.09.21 | 2 | creating project presentation for summary/discussion/etc.
| 27.09.21 | 1 | Kick-Off meeting with Prof. Schulenburg